QuizRush

Delivery Plan

Planned Development Schedule  -  March to June 2026

OICAR  |  Algebra Bernays University  |  2026

Team 1  |  Roko Pejo Bozic  |  Matej Pilic  |  Pavlo Nerekov  |  Maksym Moroz  |  Goran Jr. Skoric

# 1. Delivery Overview

Development is structured into 6 two-week sprints followed by a final integration and presentation phase. The schedule runs from 10 March to 15 June 2026, aligned with the OICAR course timeline.

Each sprint has a defined focus area, a set of deliverables, and a review checkpoint. Sprint 1 is used to finalise the technical stack, set up the development environment, and establish the CI/CD pipeline before any feature work begins.

# 2. Sprint Plan

| Sprint | Dates | Focus | Key Deliverables |
| --- | --- | --- | --- |
| S1 | 10-23.03.2026 | Architecture & Setup | DB schema, project skeleton, JWT auth, CI/CD pipeline, tech stack decision |
| S2 | 24.03-06.04.2026 | Core API | Quiz CRUD, user management, game session API, unit tests |
| S3 | 07-20.04.2026 | Real-Time + Web Basics | SignalR GameHub, host view, player join flow, live question display |
| S4 | 21.04-04.05.2026 | Web App Complete | Full host dashboard, leaderboard, quiz builder, account pages |
| S5 | 05-18.05.2026 | Mobile App | Android app: join flow, live gameplay, leaderboard, account login |
| S6 | 19.05-01.06.2026 | Polish + Analytics | Mobile host view, statistics, bug fixes, documentation |
| Final | 02-15.06.2026 | Integration & Presentation | End-to-end testing, demo preparation, final documentation |

# 3. Sprint Detail

## Sprint 1  |  10 - 23 March 2026  |  Architecture & Setup

The goal of Sprint 1 is to establish the full development foundation before any feature work begins. The team will make final technology decisions, configure the repository, and ensure every developer can build and run the project locally.

- Finalise technology stack choices (backend, frontend, mobile, database)

- Set up GitHub repository with Git Flow branching strategy

- Define database schema and create initial Entity Framework migrations

- Configure Docker Compose for local development environment

- Set up GitHub Actions CI pipeline with build and lint checks

- Implement JWT authentication (register, login, token refresh)

- Deploy basic API skeleton to staging environment

## Sprint 2  |  24 March - 6 April 2026  |  Core API

Sprint 2 focuses on the backend API - all the non-real-time endpoints that support quiz management and user accounts. The result will be a fully testable REST API with documented endpoints.

- Quiz CRUD: create, read, update, delete quizzes and questions

- User profile management and account settings

- Game session API: create session, generate PIN, retrieve results

- API documentation via Swagger / OpenAPI

- Unit tests for all service-layer logic

## Sprint 3  |  7 - 20 April 2026  |  Real-Time + Web Basics

Sprint 3 introduces the SignalR GameHub and the core web UI flows. By the end of this sprint, a host and players should be able to run a complete quiz session end-to-end on the web.

- SignalR GameHub: JoinGame, StartGame, NextQuestion, SubmitAnswer, EndGame

- Host web view: session launch, game control panel, question display

- Player web view: PIN entry, join screen, answer submission, result feedback

- Live leaderboard updates after each question

## Sprint 4  |  21 April - 4 May 2026  |  Web App Complete

Sprint 4 completes the web frontend. All host and player journeys are fully functional, including the quiz builder and account management pages.

- Quiz builder UI: drag-and-drop question editor, image support

- Host dashboard: quiz library, session history, analytics overview

- Player account: game history, personal stats, saved results

- Responsive design polish for mobile web browsers

- Cross-browser compatibility testing (Chrome, Firefox, Safari, Edge)

## Sprint 5  |  5 - 18 May 2026  |  Mobile App

Sprint 5 builds the native Android app for players. The app is planned to share the same backend API and, where possible, client code with the web frontend to reduce duplication. The exact mobile framework will be chosen in Sprint 1.

- PIN entry and game join flow on Android

- Live gameplay: countdown timer, answer options, result feedback

- Live leaderboard display

- User account login and registration in the mobile app

- Push notification support for session invites (stretch goal)

## Sprint 6  |  19 May - 1 June 2026  |  Polish + Analytics

Sprint 6 focuses on quality, stability, and statistics features. The aim is a releasable, stable product with comprehensive documentation.

- Mobile host view: ability to host a session from the mobile app

- Statistics dashboard: per-quiz analytics, question difficulty analysis

- Performance testing under simulated load (target: 100 concurrent players)

- Bug fixes from Sprint 4-5 regression testing

- Full API and code documentation

## Final Phase  |  2 - 15 June 2026  |  Integration & Presentation

The final phase covers end-to-end integration testing, demo preparation, and final submission materials.

- Full end-to-end test suite covering web and mobile player flows

- Load and stress testing

- Demo environment setup (hosted staging server)

- Final project documentation and README

- Course presentation preparation

# 4. Milestones

| Milestone | Target Date | Success Criteria |
| --- | --- | --- |
| Tech stack finalised | 23 March 2026 | All team members can build and run the project locally. |
| Backend API complete | 6 April 2026 | All REST endpoints pass unit tests; Swagger docs published. |
| Web MVP | 20 April 2026 | Full quiz session runs end-to-end on the web (host + players). |
| Web app complete | 4 May 2026 | All host and player journeys functional; responsive on mobile web. |
| Mobile app complete | 18 May 2026 | Core player flows work on Android (join, play, leaderboard). |
| Feature freeze | 1 June 2026 | No new features; focus shifts to testing and documentation. |
| Final submission | 15 June 2026 | All deliverables submitted; demo environment live. |

# 5. Risks and Mitigations

Mobile development complexity: building a native Android app introduces additional complexity compared to web. Mitigation: Sprint 5 is dedicated entirely to mobile, and the framework decision in Sprint 1 will account for the team's available expertise.

Real-time synchronisation: live game logic can be prone to race conditions under high concurrency. Mitigation: the real-time hub will be designed with clear state transitions; concurrency edge cases will be tested in Sprint 3.

Tech stack uncertainty: final technology choices are not locked until Sprint 1. This is intentional - the team will evaluate options and choose based on fit rather than committing prematurely.

Time constraints: the team is working part-time alongside coursework. Mitigation: stretch goals (e.g., mobile push notifications) are clearly identified and can be dropped without affecting core deliverables.